## Sheet1
Story ID | Story Name | Description | Priority (MoSCoW) | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date) | Story points
Epics01a | Kids' virtual bank account creation | As a kid, I want to create a new virtual bank account including current account and saving account, so that I can start managing my finances. | Must have | 1 | · Verify that new visual bank accounts can be successfully created when children enter the child user interface. · Verify that current account and saving account can be created simutaneously after registering. |  | April 1st | April 2nd | 1 | Epics01: Kids' Account Management
Epics01b | Account information management | As a kid, I want to view and edit my account details, so that I can keep my information up to date. | Must have | 2 | · Verify that children's account details such as account name and profile picture can be viewed and updated in the virtual bank. | When kids create an account, they need to enter their information(Epics01a). On this basis, kids should be able to change their own information. | April 15th | April 20th | 3
Epics02a | Parents' account creation | As a parent, I want to create a parental account in the virtual bank, so that I can supervise my children's financial activities. | Must have | 1 | · Verify that new virtual bank accounts can be created successfully by parents. · Verify that parents' accounts can perform basic operations. |  | April 1st | April 2nd | 1 | Epics02: Parents' Management of their Children's Accounts
Epics02b | Task setting | As a parent, I want to set tasks or activities for my children to earn money, so that I can help them learn the value of earning and saving. | Must have | 1 | · Verify that new tasks for the child can be set successfully by parents. · Verify that different reward amounts or virtual currencies for completing different tasks can be set from parents' account. |  | April 3rd | April 8th | 5
Epics02c | Parent inquiry | As a parent, I want to view my child's account balance and check the changes of their accounts, so that I can take charge of my child's account status. | Should have | 2 | · Verify that parents can see their children's balances and investments in their accounts. · Verify that parents can set limits on their children's investments. | This is a function just for parents, as opposed to children viewing account information on their own(Epics04a). | April 15th | April 20th | 3
Epics02d | Parent notification system | As a parent, I want to receive important notifications about my child's account, so that I can stay informed about their financial activities. | Should have | 2 | · Verify that the system notifies parents in real time when changes occur to their child's account, such as changes in account balances and task completion. · Verify that parents can click to confirm the completion of the task after receiving the notification |  | April 15th | April 25th | 5
Epics03a | Deposit | As a kid, I want to deposit the virtual currency I earn from completing tasks, so that I can increase my savings. | Must have | 1 | · Verify that children can enter the amount of money they want to deposit. · Verify that application validates and accepts the deposit amount. |  | April 3rd | April 5th | 2 | Epics03: Balance Management
Epics03b | Withdrawal | As a kid, I want to withdraw the virtual currency I earn from completing tasks, so that I can use it for spending or saving. | Must have | 1 | · Verify that children can enter the amount of money they want to withdraw. · Verify that application validates and processes the withdrawal request. |  | April 3rd | April 5th | 2
Epics03c | Balance tracking | As a kid, I want to track the balance in my virtual bank account, so that I can monitor my savings progress. | Must have | 1 | · Verify that the balance updates in real-time when deposits or withdrawals are made. · Verify that children can easily access a detailed breakdown of their account balance. |  | April 3rd | April 6th | 3
Epics03d | Multi-currency support | As a kid, I want to hold multiple currencies in my account and convert them to other types of currencies, so that I can use them in various situations and manage my finances efficiently. | Want to have | 4 | · Verify that children can check the balance of different currencies in their account. · Verify that children can convert their balance from one currency to another for a fee. |  | May 13rd | May 24th | 13
Epics04a | Transactions | As a kid, I want to view historical transaction records, so that I can better track my finances. | Must have | 1 | · Verify that children can access a list of all transactions made on the account. · Verify that each transaction entry includes details such as date, amount, type, deposit/withdrawal, and transaction description. | This is a function just for children. Parents cannot view their child's account information through this feature. | April 3rd | April 8th | 5 | Epics04: Transaction Management
Epics04b | Customized filtering and sorting | As a kid, I want to customize filtering and sorting options for my transaction records, so that I can easily find and manage my financial data. | Should have | 2 | · Verify that kids can select different filtering conditions in the transaction record page, such as date range, transaction type and so on. · Verify that kids can sort the transaction records according to different fields, such as transaction date, amount, etc., in order to sort the transaction records according to their needs. | For example, if a kid wants to query their transaction records for a certain month, they can use this function to enter the time of a certain month as a filter. | April 15th | April 20th | 3
Epics04c | Categorize and label transactions | As a kid, I want to categorize and label transaction records, so that I can easily search and manage the uses and sources of various expenditures and incomes. | Could have | 2 | · Verify that kids can add customized classification tags such as Food, Transportation, Entertainment, etc. for each transaction or select a preset classification. · Verify that kids can view the corresponding transaction records according to different classification tags. · Verify that kids can add notes or descriptions to transactions to record information about each transaction in more detail. | For example, a kid can categorize transactions into living, learning, and food. The consumption of meals is classified as food. | April 15th | April 20th | 3
Epics04d | Adding friends | As a kid, I want to add friends to my virtual bank, so that I could engage in financial activities with my peers. | Should have | 3 | · Verify that kids can search and find the friends they want to add by entering their username or other unique identifying information. · Verify that when kid sends a friend request, the recipient should be notified and able to accept or reject the request. |  | April 29th | May 6th | 8
Epics04e | Online virtual money transfers | As a kid, I want to transfer virtual money from my account to another accounte, so that I send money to my friends. | Should have | 3 | · Verify that kids can select friends and enter the amount of virtual currency to send. · Verify that the system can be able to accurately and securely handle the sending of virtual currency transactions. | Based on adding friends(Epics04d). | April 29th | May 3rd | 5
Epics04f | Gift money | As a kid, I want to send money to my friends, or receive money as gifts, so that I can deepen the friendship with them. | Want to have | 4 | · Verify that kids can select the gift function and enter the corresponding amount. · Verify that kids can choose to receive the gift money, which will be automatically credited to the balance. | This is a different function from money transfer(Epics04e). Transfers do not need to be received, but gifts need to be received manually. | May 13rd | May 24th | 13
Eipcs05a | Saving goals | As a kid, I want to set my own savings goals and track progress towards those goals, so that I can effectively manage and achieve my financial objectives. | Must have | 1 | · Verify that kids can create multiple savings goals with specific target amounts and target dates. · Verify that each savings goal entry includes details such as goal name, target amount, target date, and current progress. |  | April 3rd | April 5th | 2 | Epics05: Goal Management
Eipcs05b | Goal-setting reminders | As a kid, I want to set priorities and reminders for each savings goal, so that I can stay focused on and get reminded of achieving them. | Could have | 2 | · Verify that the system is able to remind kids when they are close to their target date based on the target deadline they have set. |  | April 15th | April 25th | 5
Eipcs06 | Investment product | As a kid, I want to choose to invest part of my balance in investment products and see the profit and loss status, so that I can learn about investments and potentially increase my savings. | Could have | 3 | · Verify that children can choose to use the balance to purchase investment products and the balance will be deducted accordingly. · Verify that children can check the rise and fall of investment products at any time. |  | April 29th | May 10th | 13
Eipcs07 | Community | As a kid, I want to join a community and participate in discussions in community forums about my virtual bank, so that I can share my goals with other children and learn from their experiences. | Want to have | 4 | · Verify that children are able to join the community through simple steps and successfully browse the community pages. · Verify that children can search the community and find discussion threads or topics of interest. · Verify that children can post their own savings goals, participate in discussions and interact with other children. |  | May 13rd | May 19th | 8